## Instructions
Consultancy Income Forecast
Percentage-of-completion revenue recognition · GBP (£) · Financial year September–August · XLOOKUP formulas
How this workbook works
Every engagement is confirmed work with a Matter Code and an agreed fixed fee. Each month the engagement manager (EM) sets the cumulative % complete; the workbook recognises the corresponding slice of the fee. Actual net fee income (NFI) is pulled automatically from the Month-End Provisions tab and compared against the forecast, and any variance is flagged.
The five tabs
1. Matters Register — master list of engagements (Matter Code, client, EM, total fixed fee, dates, status). Add a row here first for every new confirmed engagement.
2. Forecast Log — the working record, one row per engagement per month. You enter the Matter Code, the Month, and the cumulative % complete. Everything else calculates. This is the permanent, append-only history — never overwrite a past month's row; add a new row for the new month.
3. Month-End Provisions — paste your monthly NFI provisions extract here (Matter Code, Month, NFI Amount). The Forecast Log reads actuals from this tab by matching Matter Code + Month.
4. Dashboard — portfolio roll-up by month, by engagement and by EM, with a forecast-vs-actual chart and an Open Variances tracker.
5. Instructions — this page.
Monthly routine
a. Paste the latest NFI provisions into Month-End Provisions.
b. In the Forecast Log, add one new row per active engagement for the new month and enter the cumulative % complete.
c. Review the Variance column: red = actual came in UNDER your forecast; amber = actual came in OVER your forecast.
d. Re-allocate next month: use Cumulative Actual and Remaining Fee to re-base your % complete so the remaining fee is re-spread across the remaining months. The workbook flags the variance; the EM decides how to re-spread it.
e. Record the reforecast on the FLAGGED month's row: set Variance Status (Reforecast / Accepted), plus Reforecast By and Reforecast Date. This is the audit trail.
Tracking reforecasts
The Forecast Log's right-hand columns show whether each flagged variance has been actioned: Reforecast Entered? auto-detects whether a later month's row exists; Outstanding? shows YES (red) for any variance not yet signed off; Action Note says what's needed. Use the header AutoFilter to filter Outstanding? = YES or by Engagement Manager. The Dashboard's Open Variances panel counts outstanding items overall and per EM.
Colour key
Blue text on pale-yellow fill = cells you fill in. Black = calculated, do not edit. Green = pulled from another tab. Red / amber fills = under / over variance and outstanding-reforecast flags.
Notes
· % complete is stored as a fraction (enter 25% or 0.25, not 25). · All amounts are GBP. · Dates are the first of the month (shown as Sep-2026). · Demo engagements M-1001/1002/1003 are examples — delete them once you add your own.

## Matters Register
Matters Register
One row per confirmed engagement. Blue cells are inputs.
Matter Code | Client | Engagement Name | Engagement Manager | Total Fee (£) | Start Date | Expected End Date | Status
M-1001 | Aurora Retail Group | Supply Chain Diagnostic | Priya Shah | 120000 | 2026-09-01 | 2027-02-28 | Active
M-1002 | Northwind Energy | Cost Transformation | James Okoro | 90000 | 2026-10-01 | 2027-03-31 | Active
M-1003 | Meridian Health | Operating Model Review | Priya Shah | 60000 | 2026-09-01 | 2026-12-31 | Active

## Forecast Log
Forecast Log — permanent monthly record
Append one row per engagement per month. Enter Matter Code, Month and Cumulative % Complete (blue). Everything else calculates.
Matter Code | Month | Total Fee (£) | Cum % Complete | Forecast Cum Revenue (£) | Forecast Recognised This Month (£) | Actual NFI This Month (£) | Variance (£) | Cumulative Actual to Date (£) | Remaining Fee (£) | Engagement Manager | Variance Status | Reforecast By | Reforecast Date | Reforecast Entered? | Outstanding? | Action Note
M-1001 | 2026-09-01 | 120000 | 10% | 12000 | 12000 | 12000 | 0 | 12000 | 108000 | Priya Shah
M-1001 | 2026-10-01 | 120000 | 25% | 30000 | 18000 | 15000 | -3000 | 27000 | 93000 | Priya Shah |  |  |  | Yes | YES | Reforecast entered — confirm sign-off
M-1001 | 2026-11-01 | 120000 | 45% | 54000 | 24000 | 26000 | 2000 | 53000 | 67000 | Priya Shah |  |  |  | No | YES | Awaiting reforecast
M-1002 | 2026-10-01 | 90000 | 15% | 13500 | 13500 | 13500 | 0 | 13500 | 76500 | James Okoro
M-1002 | 2026-11-01 | 90000 | 30% | 27000 | 13500 |  |  | 13500 | 76500 | James Okoro
M-1003 | 2026-09-01 | 60000 | 20% | 12000 | 12000 | 12000 | 0 | 12000 | 48000 | Priya Shah
M-1003 | 2026-10-01 | 60000 | 40% | 24000 | 12000 | 11000 | -1000 | 23000 | 37000 | Priya Shah | Reforecast | PS | 2026-11-04 | Yes |  | Signed off: Reforecast
M-1003 | 2026-11-01 | 60000 | 65% | 39000 | 15000 |  |  | 23000 | 37000 | Priya Shah

## Month-End Provisions
Month-End Provisions (Net Fee Income)
Paste your monthly NFI provisions extract here.
Matter Code | Month | NFI Amount (£)
M-1001 | 2026-09-01 | 12000
M-1001 | 2026-10-01 | 15000
M-1001 | 2026-11-01 | 26000
M-1002 | 2026-10-01 | 13500
M-1003 | 2026-09-01 | 12000
M-1003 | 2026-10-01 | 11000

## Dashboard
Portfolio Dashboard
Financial year September 2026 – August 2027.
Month | Forecast (£) | Actual NFI (£) | Variance (£) | Matter Code | Client | Engagement Manager | Total Fee (£) | Forecast to Date (£) | Actual to Date (£) | Remaining Fee (£) | % Recognised | Open Var (#)
2026-09-01 | 24000 | 24000 | 0 | M-1001 | Aurora Retail Group | Priya Shah | 120000 | 54000 | 53000 | 67000 | 44.17% | 2
2026-10-01 | 43500 | 39500 | -4000 | M-1002 | Northwind Energy | James Okoro | 90000 | 27000 | 13500 | 76500 | 15% | 0
2026-11-01 | 52500 | 26000 | -26500 | M-1003 | Meridian Health | Priya Shah | 60000 | 39000 | 23000 | 37000 | 38.33% | 0
2026-12-01 | 0 | 0 | 0
2027-01-01 | 0 | 0 | 0
2027-02-01 | 0 | 0 | 0
2027-03-01 | 0 | 0 | 0
2027-04-01 | 0 | 0 | 0
2027-05-01 | 0 | 0 | 0
2027-06-01 | 0 | 0 | 0
2027-07-01 | 0 | 0 | 0
2027-08-01 | 0 | 0 | 0
Total | 120000 | 89500 | -30500
Open Variances — flagged but not yet reforecast
Open items (#) | 2
Open value (£, net) | -1000
Oldest open month | 2026-10-01
By Engagement Manager (add/remove names as needed)
|  |  |  | Engagement Manager | Forecast to Date (£) | Actual to Date (£) | Open (#)
|  |  |  | Priya Shah | 93000 | 76000 | 2
|  |  |  | James Okoro | 27000 | 13500 | 0